## Dates
event | color | start | group
SAP Approval | SAP | 2018-05-10 | Vineyard Wind
COP Submitted | COP Submit | 2017-12-01 | Vineyard Wind
COP Withdrawn | COP Other | 2020-12-01 | Vineyard Wind
SAP Filled | SAP | 2017-03-01 | Vineyard Wind
SAP Revision | SAP | 2017-11-01 | Vineyard Wind
SAP Revision | SAP | 2017-10-01 | Vineyard Wind
SAP Revision | SAP | 2017-07-01 | Vineyard Wind
SAP Completed | SAP | 2017-11-21 | Vineyard Wind
DEIS Release | DEIS Release | 2018-12-07 | Vineyard Wind
End of Public comment on DEIS | Comment End | 2019-02-22 | Vineyard Wind
Supliment to DEIS | DEIS Release | 2020-06-12 | Vineyard Wind
Recinded Temporary COP Withdrawl | COP Other | 2021-01-22 | Vineyard Wind
NOI on EIS Preperation | NOI EIS | 2018-03-30 | Vineyard Wind
End of Public comment | Comment End | 2018-04-30 | Vineyard Wind
COP Approval Letter | COP Approval | 2021-07-15 | Vineyard Wind
ROD Release | ROD Release | 2021-05-12 | Vineyard Wind
FEIS Avaliable | FEIS Release | 2021-03-12 | Vineyard Wind
COP Approval | COP Approval | 2022-01-22 | South Fork
ROD Release | ROD Release | 2021-11-01 | South Fork
FEIS Release | FEIS Release | 2021-08-16 | South Fork
SAP Approved | SAP | 2017-10-12 | South Fork
SAP Filled | SAP | 2016-04-01 | South Fork
SAP Ammendum | SAP | 2016-07-01 | South Fork
SAP Ammendum | SAP | 2016-09-01 | South Fork
SAP Ammendum | SAP | 2016-11-01 | South Fork
SAP Completed | SAP | 2016-10-01 | South Fork
COP Submitted | COP Submit | 2018-06-29 | South Fork
COP Update | COP Update | 2019-05-24 | South Fork
COP Update | COP Update | 2020-02-13 | South Fork
COP Update | COP Update | 2020-07-22 | South Fork
COP Update | COP Update | 2021-05-07 | South Fork
Project Pause | Other | 2019-04-08 | South Fork
NOI for EIS | NOI EIS | 2018-10-19 | South Fork
End Public Comment period | Comment End | 2018-11-19 | South Fork
DEIS Release | DEIS Release | 2021-01-04 | South Fork
ROD Approved | ROD Release | 2023-07-05 | Ocean Wind 1
SAP Filled | SAP | 2017-09-15 | Ocean Wind 1
SAP Revision | SAP | 2017-11-01 | Ocean Wind 1
SAP Revision | SAP | 2018-01-01 | Ocean Wind 1
SAP Revision | SAP | 2018-02-01 | Ocean Wind 1
NOI to Prepare EIS | NOI EIS | 2021-03-30 | Ocean Wind 1
End of Public comment for DEIS | Comment End | 2022-08-23 | Ocean Wind 1
DEIS NOA | DEIS Release | 2022-06-24 | Ocean Wind 1
FEIS NOA | FEIS Release | 2023-05-26 | Ocean Wind 1
Updated COP Submitted | COP Update | 2023-04-24 | Ocean Wind 1
NOA on FEIS | FEIS Release | 2023-07-17 | Revolution Wind
Lease area reassignment | Other | 2020-03-23 | Revolution Wind
SAP Approved | SAP | 2017-10-12 | Revolution Wind
SAP Filled | SAP | 2016-04-01 | Revolution Wind
SAP Revision | SAP | 2016-07-01 | Revolution Wind
SAP Revision | SAP | 2016-09-01 | Revolution Wind
SAP Revision | SAP | 2016-11-01 | Revolution Wind
SAP Completed | SAP | 2016-10-07 | Revolution Wind
COP Submitted | COP Submit | 2020-03-13 | Revolution Wind
COP Update | COP Update | 2021-04-29 | Revolution Wind
COP Update | COP Update | 2022-07-21 | Revolution Wind
COP Update | COP Update | 2023-03-01 | Revolution Wind
NOI on EIS | NOI EIS | 2021-04-30 | Revolution Wind
End of Public comment period | Comment End | 2021-05-30 | Revolution Wind
NOA on DEIS | DEIS Release | 2022-08-29 | Revolution Wind
NOI on EIS | NOI EIS | 2021-07-30 | Kittyhawk
End of Public comment period | Comment End | 2021-08-30 | Kittyhawk
SAP Submitted | SAP | 2019-09-18 | Kittyhawk
SAP Revision | SAP | 2019-11-04 | Kittyhawk
SAP Revision | SAP | 2019-11-25 | Kittyhawk
SAP Revision | SAP | 2019-12-16 | Kittyhawk
SAP Revision | SAP | 2020-01-25 | Kittyhawk
SAP Revision | SAP | 2020-02-20 | Kittyhawk
SAP Approval | SAP | 2020-04-08 | Kittyhawk
NOA on DEIS | DEIS Release | 2022-12-12 | Sunrise Wind
End of Public Comment | Comment End | 2023-02-14 | Sunrise Wind
Reassgnment from Bay State wind | Other | 2020-09-03 | Sunrise Wind
Lease Consolidation completed | Other | 2021-03-15 | Sunrise Wind
COP Submitted | COP Submit | 2020-09-01 | Sunrise Wind
COP Update | COP Update | 2022-08-18 | Sunrise Wind
NOI to Prepare EIS | NOI EIS | 2021-08-31 | Sunrise Wind
NOI Correction | NOI EIS | 2021-09-03 | Sunrise Wind
End of Comment Period | Comment End | 2021-10-04 | Sunrise Wind
End of Public comment period | Comment End | 2023-04-18 | Mayflower / South Coast
Start of Lease | Other | 2019-04-01 | Mayflower / South Coast
SAP Submitted | SAP | 2019-12-12 | Mayflower / South Coast
SAP Approved | SAP | 2020-05-26 | Mayflower / South Coast
NOI to Prepare EIS | NOI EIS | 2021-11-01 | Mayflower / South Coast
NOA for DEIS | DEIS Release | 2023-02-13 | Mayflower / South Coast
NOA for DEIS | DEIS Release | 2022-12-12 | Coastal Virginia
End of Public comment period | Comment End | 2023-02-14 | Coastal Virginia
SAP Approval | SAP | 2017-10-12 | Coastal Virginia
SAP Submitted | SAP | 2016-03-02 | Coastal Virginia
COP Submitted | COP Submit | 2020-12-17 | Coastal Virginia
COP Update | COP Update | 2021-06-17 | Coastal Virginia
COP Update | COP Update | 2021-10-30 | Coastal Virginia
COP Update | COP Update | 2021-12-03 | Coastal Virginia
COP Update | COP Update | 2022-05-06 | Coastal Virginia
NOI to Prepare EIS | NOI EIS | 2021-07-02 | Coastal Virginia
End of Public Comment | Comment End | 2021-08-02 | Coastal Virginia
NOA for DEIS | DEIS Release | 2022-12-19 | New England Wind
End of Public comment period | Comment End | 2023-02-21 | New England Wind
partial assignment of Northern portion to vineyard wind 1 | Other | 2021-06-28 | New England Wind
Reassignment to park city wind | Other | 2021-12-14 | New England Wind
SAP Approved | SAP | 2018-05-10 | New England Wind
COP Sumitted | COP Submit | 2020-07-02 | New England Wind
COP Update | COP Update | 2021-12-01 | New England Wind
COP Update | COP Update | 2022-03-01 | New England Wind
NOI to Prepare EIS | NOI EIS | 2021-06-30 | New England Wind
End of Comment Period | Comment End | 2021-12-22 | New England Wind
NOA on DEIS | DEIS Release | 2022-11-14 | Empire Wind
End of Public comment period | Comment End | 2023-01-17 | Empire Wind
SAP Approved | SAP | 2018-11-21 | Empire Wind
SAP Submitted | SAP | 2018-06-01 | Empire Wind
SAP Updates | SAP | 2018-07-01 | Empire Wind
SAP Updates | SAP | 2018-08-01 | Empire Wind
SAP Updates | SAP | 2018-10-01 | Empire Wind
SAP Completed | SAP | 2018-08-22 | Empire Wind
COP Submitted | COP Submit | 2020-01-10 | Empire Wind
COP Update | COP Update | 2021-04-14 | Empire Wind
NOI to Prepare EIS | NOI EIS | 2021-06-24 | Empire Wind
End of Comment Period | Comment End | 2021-07-26 | Empire Wind
NOA on DEIS | DEIS Release | 2023-05-15 | Atlantic Shores South
End of public comment | Comment End | 2023-07-03 | Atlantic Shores South
Lease Reassignment | Other | 2018-12-04 | Atlantic Shores South
Lease Reassignment | Other | 2019-08-13 | Atlantic Shores South
Spliting Project Area | Other | 2021-04-19 | Atlantic Shores South
SAP Submitted | SAP | 2019-12-08 | Atlantic Shores South
SAP Approved | SAP | 2021-04-08 | Atlantic Shores South
COP Submitted | COP Submit | 2021-03-26 | Atlantic Shores South
COP Update | COP Update | 2023-05-03 | Atlantic Shores South
NOI on EIS | NOI EIS | 2021-09-20 | Atlantic Shores South
End Public Comment period | Comment End | 2021-11-01 | Atlantic Shores South
COP Submitted | COP Submit | 2020-12-11 | Kittyhawk
COP Submitted | COP Submit | 2019-08-15 | Ocean Wind 1
COP Submitted | COP Submit | 2021-02-15 | Mayflower / South Coast
SAP Submitted | SAP | 2018-05-10 | New England Wind

## SizesColors
Tags | Size | Color_
SAP | 1
COP Submit | 3
COP Other | 2
DEIS Release | 5
Comment End | 1
NOI EIS | 3
COP Approval | 5
ROD Release | 5
FEIS Release | 5
COP Update | 2
Other | 2